## Purification
Rough Total | 102554.68 | [10 empty] | short | 1-2 days
[12 empty] | medium | weeks
Equipment | Brand | Model | Type | Cost | Quantity |  | Extra Comments | Posession Status | Used in Build | Lead Time | Company Hassle | long | month
Non-corrosive Mass Flow Controller | Aalborg | GFC17A-BAL6-A0 | electronic | 941 | 2 |  | for H2: THERMAL MFC 316 SS PTFE/KALREZ 1/4"COMPR FTG LCD DISPLAY 0-5VDC/4-20MA Hydrogen H2 0-2 STD L/MIN STD METERING PRESS [14.7PSIA] STD TEMP [21.1øC/70øF] for Ar: THERMAL MFC ALUMINUM BUNA-N 1/4"COMPR FTG LCD DISPLAY 0-5VDC/4-20MA Argon Ar 0-2 STD L/MIN STD METERING PRESS [14.7PSIA] STD TEMP [21.1øC/70øF] | arrived | yes | long | no | very long | 2 months+
Corrosive Mass Flow Controller | Teledyne Hastings | HFC-D-302B(H) | electronic | 1655 | 1 |  | Standard output, fittings, display, working pressure, & calibration type | arrived | yes | long | no
Norman Filters Woven Mesh Filter U-91560 | Norman Filters | 4325TG-10V | piping | 1456 | 1 |  | 316SS mesh; for 1/2" tube | arrived | yes | very long | custom part
1/4" C-276 Ball Valves | Swagelok | HC-62TS4 | piping | 2866 | 2 |  |  | arrived | yes | very long | no
1/2" C-276 Ball Valves | Swagelok | HC-63TS8 | piping | 3727 | 2 |  |  | arrived | no | very long | no
Tube Furnace with Setpoint Control | ATS | 3110-8.25-16-16 | electronic | 6738 | 1 |  | Tube type construction with stainless steel shell. -Dimensions: 8.25 in. I.D. x 16 in. O.D. x 13 in. Long -Elements: Kanthal A1, embedded windings. -Furnace Temperature Rating: 800 deg. C. -Single Zone Construction, 10 in. heated length -Total Power: 5350 Watts/23.2 amps @ 230 VAC, 1Ph, 60 Hz. -End Disk: 1.5 in. thick, bore 7 in. both ends -End Caps: 1.5 in. thick, bore 7 in. both ends -(1) Thermocouple Port: Located midlength of heated zone -(1) Thermocouple, Type K, with ceramic insulator -(1) Thermocouple, Type K, connector with mounting bracket -(1 set) Support Brackets for vertical mount | arrived | yes | very long | custom part
1/2" C-276 Tubing | Swagelok | HC-T8-S-049-20P | piping | 47.34 | 20 | ft |  | arrived | yes | long | no
1/4" C-276 Tubing | Swagelok | HC-T4-S-035-20P | piping | 25.36 | 20 | ft |  | arrived | yes | long | no
2L PTFE Scrubber Vessel | VWR | 89026-028 | scrubber | 183.95 | 1 |  |  | arrived | no | medium | yes
5L PTFE Scrubber Vessels | VWR | 89026-020 | scrubber | 299.59 | 2 |  |  | arrived | yes | medium | yes
1/4" ID PTFE Tubing | VWR/Thermo Scientific | 63014-713 | scrubber | 4.81 | 25 | ft |  | arrived | no | medium | yes
HF Fumes Detector | VWR/GfG Instrumentation | 76334-718 | electronic | 1468.45 | 2 |  | Range: 0-10 ppm, Resolution: 0.1 ppm | arrived | yes | long | yes
HF Gas Cylinder | Linde | UN1052 | gas | 2702.84 | 1 |  | 4.5 L (3.8kg) filled, 30" tall with valve, 4.5" diameter | arrived | yes | long - very long | supply issues
Ar Gas Cylinder | Brazos Welding |  | gas |  |  |  |  | arrived | yes | short | no
Scale | Mettler Toledo | H-5275 | electronic | 895 |  |  | Mettler-Toledo™ BC60 Parcel Scale - 150 lbs x .05 lb | arrived | yes | medium | no
Thermocouple | Pyromation | GP02 | electronic | 285.1 | 1 |  | K-type, 16in long sheath, 1/4in diameter sheath, 1/2in screw connection, 4-20 mA output, 0-900C range | arrived | no | medium | no
3/4" to 1/2" 316SS Union | Swagelok | SS-1210-6-8 | piping | 41.1 | 6 |  |  | arrived | 1 | short | no
1/2" to 3/8" 316SS Union | Swagelok | SS-810-6-6 | piping | 26.9 | 9 |  |  | arrived | 2 | short | no
1/2" to 1/4" 316SS Union | Swagelok | SS-810-6-4 | piping | 27 | 9 |  |  | arrived | 2 | short | no
3/8" to 1/4" 316SS Union | Swagelok | SS-600-6-4 | piping | 17.4 | 5 |  |  | arrived | 1 | short | no
1/2" C-276 Union | Swagelok | HC-810-6 | piping | 526.9 | 1 |  |  | arrived | yes | long | no
1/4" 316SS Cross Union | Swagelok | SS-400-4 | piping | 45.3 | 6 |  |  | arrived | 1 | short | no
1/2" OD x 25" L x 1/8" T Ni-200 Tube | Magellan Metals |  | piping | 1605 | 1 |  |  | arrived | yes | long | no
3/8" OD x 23" L x 1/16" T Ni-200 Tube | Magellan Metals |  | piping | 797 | 2 |  |  | arrived | yes | long | no
1/8" OD x 4" L x 1/32" T Ni-200 Tube | Magellan Metals |  | piping | 775 | 1 |  |  | arrived | yes | long | no
28" L x 18" W x 1/8" T Ni-200 Plate | Magellan Metals |  | vessel | 830 | 1 |  |  | arrived | yes | medium | no
8" FOD x 16" L 316SS Half Nipple | Kurt Lesker |  | vessel | 2248.55 | 1 |  | 8"OAL, 10"CF FIXED FLANGE, 8"OD X .120" WALL TUBING. OPEN END OF TUBE WILL BE UNCAPPED. FLANGE SIDE OF TUBING WILL BE BLANKED MATERIAL: 316LN SS FLANGE WITH TUBING/DISC FROM 316/316L SS FINISH: POLISHED TUBE. CAPPED END OF TUBE WILL BE EITHER DA FINISH OR BRUSH FINISH. | arrived | yes | long | yes & custom part
316SS Plate | McMaster Carr |  | vessel | 114.7 | 1 |  | 8" L x 8" W x 1/4" T | arrived | yes | short | no
Residual Gas Analyzer | Stanford Research Systems |  | electronic | 3890.65 | 1 |  | RGA 100 | arrived | yes | medium | no
Fire Brick | Lynn Manufacturing | K-23 | heating | 9.33 | 12 |  | 9" x 4.5" x 2.5" | arrived | yes | short | no
Ceramic Fiber Blanket | Lynn Manufacturing |  | heating | 24.9 | 1 |  | 25" x 24" x 0.5" | arrived | yes | short | no
C-276 Rupure Disk Housing | Alpha Process Sales |  | vessel | 1896 | 3 |  | 1/2" Swagelok Connection, 80 psi, 50C, 316SS outlet | arrived | yes | very long | yes & custom part
^ machining costs | BS&B Safety Systems |  | vessel | 1300 | 1 |  |  |  |  | very long | yes & custom part
Thermocouple | Parr Instruments | A472E5 | electronic | 80 | 1 |  | Thermocouple, type-J, 21-1/2” 1/8, T316 | arrived | yes | short | no
Heating Tape | Brisk Heat | TBIH051-040-LSE | heating | 125 | 1 |  | 120 VAC, max temp 900°F, leads same ends, 2 ft | arrived | yes | medium | yes
PTFE Bottle | Lab Depot | 314874 | scrubber | 245.61 | 1 |  | 500 mL | arrived | yes | medium | no
Hydrogen Generator | Peak Scientific | 3301768 | gas | 23623.2 | 1 |  | Trace 1200cc, 100-230V, 8L bottle | arrived | yes | very long | no
1/4" 316SS Needle Valve | Swagelok | SS-1RS4 | piping | 80.01 | 1 |  |  | arrived | yes | short | no
1/4" 316SS Check Valve | Swagelok | SS-4C-KZ-1 | piping | 98.91 | 3 |  | Kynar Seals, 1 psi | arrived | yes | medium | no
Turbo Pump | Leybold | Turbovac 90i / DN 63 CF | vacuum | 4169 | 1 |  | 4.5" CF flange inlet, KF16 outlet | arrived | yes | long | no
Turbo Pump Power Supply and Cables | Leybold | Turbo.power Integra | vacuum | 777.15 | 1 |  |  | arrived | yes | long | no
1/2" 316SS Needle Valve | Swagelok | SS-6NBS8(-G) | piping | 253 | 5 |  | 2 have grafoil packing | arrived | yes | short | no
0.3 mm ID PTFE Tubing | Omnifit |  | piping | 64.81 | 1 |  | 20m length, 1/16" OD | arrived | yes | medium | no
1/4" Kynar Tubing | Ultra Pure Products | RFPVDF-.187-250 | piping | 1.41 | 20 | ft |  | arrived | yes | medium | no
Oxygen Trap | VWR/Restek | 20638 | gas | 372.8 | 2 |  | 1/4" swagelok connections | arrived | yes | medium | yes
1/4" to 1/16" 316SS Union | Swagelok | SS-400-6-1FGC | piping | 38.22 | 2 |  |  | arrived | yes | short | no
4.5" CF 304SS Blank Flange | Kurt Lesker | F0450X000N | vacuum | 59.05 | 1 |  |  | arrived | yes | medium | no
KF16 Flexible Metal Hose | LDS Vacuum | NW16-MH48-VE | vacuum | 214 | 1 |  | 48" length, Sealing Rings and clamps included | arrived | yes | medium | no +
KF16 to 1/4" Swagelok Adapter | LDS Vacuum | NW16x25SWG-VE | vacuum | 57 | 2 |  | Sealing Rings and clamps included | arrived | yes | medium | no +
KF25 to KF16 Union | LDS Vacuum | NW25x16-CR-VE | vacuum | 49 | 1 |  | Sealing Rings and clamps included | arrived | yes | medium | no +
KF25 to 1/4" Swagelok Adapter | LDS Vacuum | NW25x25SWG-VE | vacuum | 69 | 1 |  | Sealing Rings and clamps included | arrived | yes | medium | no +
2.75" CF 304SS Blank Flange | LDS Vacuum | 275-000-VE | vacuum | 21 | 1 |  | Nuts, bolts, and washers included | arrived | yes | medium | no +
2.75" CF to 1/4" Swagelok Adapter | LDS Vacuum | 275xSWG-25 | vacuum | 69 | 1 |  | Nuts, bolts, and washers included | arrived | yes | medium | no +
4.5" CF to 2.75" CF Reducer | LDS Vacuum | 450x275-150-0-T1 | vacuum | 104 | 1 |  | Nuts, bolts, and washers included | arrived | yes | medium | no +
4.5" CF to 2.75" CF Reducing Cross | LDS Vacuum | 450x275-RDX | vacuum | 300 | 1 |  | Nuts, bolts, and washers included | arrived | yes | medium | no +
KF16 to 1/2" Swagelok Adapter | LDS Vacuum | NW16x50SWG-VE | vacuum | 73 | 2 |  | Sealing Rings and clamps included | arrived | yes | medium | no +
KF25 to KF16 Flexible Metal hose | LDS Vacuum | NW25x16-MH20-VE | vacuum | 162 | 1 |  | 20" length, Sealing Rings and clamps included | arrived | no | medium | no +
Roughing Pump | A-VAC industries | Edwards RV5 | vacuum | 1630 | 1 |  | Rebuilt, 4.1 cfm, 1ph, 115/230V | arrived | yes | medium | no +
1/4" Compression to 3/8" Male NPT PTFE Union | VWR/Ace Glass | 12710-12 | scrubber | 52.5 | 2 |  |  | arrived | yes | long | no
1/4" 316SS Check Valve | Swagelok | SS-CHS4-1 | piping | 61.4 | 3 |  | 1 psi | arrived | no | short | no
1/4" Swagelok to 1/4" Male NPT 316SS Union | Swagelok | SS-400-1-4 | piping | 7.9 | 10 |  |  | arrived | no | short | no
1/4" Swagelok 316SS Elbow Union | Swagelok | SS-400-9 | piping | 17.7 | 10 |  |  | arrived | yes | short | no
1/4" Swagelok 316SS Tee Union | Swagelok | SS-400-3 | piping | 24.9 | 10 |  |  | arrived | yes | short | no
1/4" 316SS Ball Valve | Swagelok | SS-42GS4 | piping | 98.76 | 2 |  | 1 piece, 0.6 Cv | arrived | yes
1/4" 316SS Ball Valve | Swagelok | SS-43GS4 | piping | 99.4 | 5 |  | 1 piece, 1.4 Cv | arrived | yes (get more) | short | no
1/4" 316SS 3-way Ball Valve | Swagelok | SS-43GXS4 | piping | 125 | 5 |  | 1 piece, 0.9 Cv | arrived | no | short | no
1/2" 316SS Ball Valve | Swagelok | SS-45S8 | piping | 234.1 | 3 |  | 1 piece, 12 Cv | arrived | 2 | short | no
1/2" C-276 Needle Valve | Swagelok | HC-6NBS8-G-HC | piping | 2024.26 | 2 |  | Grafoil packing | arrived | yes | short | no
1/4" 316SS Tubing | Swagelok | SS-T4-S-035-20 | piping | 3.12 | 60 | ft | in 6ft sections, 0.035" wall thickness, 5100 psi | arrived | yes | short | no
3/4" Swagelok 316SS Union | Swagelok | SS-1210-6 | piping | 42.2 | 5 |  |  | arrived | no | short | no
C-276 Plate | Magellan Metals |  | vessel | 315 | 2 |  | 0.25" x 2.5" x 6" | arrived | yes | medium | no
1/4" CS Tube | Earle M. Jorgensen Co |  | piping | 6.25 | 40 | ft |  | arrived | no | medium | yes
Corrosive Gas Regulator | Matheson |  | gas | 2201.24 | 1 |  | Monel, Single Stage, 1-50 psi, 660 CGA | arrived | yes | long | yes
KF16 Ball Valve | Kurt Lesker | BVB0075MVQF | vacuum | 345 | 1 |  |  | arrived | yes | long | no
Ion Pressure Gauge | Kurt Lesker | KJLC354401YF | electronic | 1308 | 1 |  | 2.75" CF connection | arrived | yes | medium | no
I/O Controller | National Instruments | 781441-01 | electronic | 2745.9 | 1 |  | NI USB-6353, X Series DAQ (32 AI, 48 DIO, 4 AO) & Power Cord, AC, U.S., 120 VAC, 2.3 meters | ordered | yes | very long | Custom part
1/4" to 1/8" 316SS Union | Swagelok | SS-400-6-2 | piping | 14.18 | 1 |  | for connecting up the hydrogen generator | arrived | yes | short | no
Heating Tape w/ Controller | Brisk Heat | HSTAT051004 | heating | 199.56 | 1 |  | 4 ft long, 0.5 in wide, 120 V, 144 Watt, 10-218° C | arrived | yes | short | no
Ceramic Fiber Insulation | Unitherm | CF8-5-24x60in | heating | 40.53 | 1 |  | 5 ft long, 2 ft wide, 0.5 in thick | arrived | no | short | no
1/4" Female NPT to Swagelok Monel adapter | Swagelok | M-400-7-4 | piping | 44.35 | 1 |  |  | ordered | yes | short | no

## Connections
DEVICE | MANUFACTURER | INPUT | OUTPUT | RESOLUTION | SCAN RATE | CONNECTION | PURPOSE | MANUAL / DATASHEET
GFC17, S#553674-1 | Aalborg | 0-5 V | 4-20 mA | ±0.01 L/min | 1 sec | 15-pin | Control the flow of Ar into the system | https://www.aalborg.com/images/file_to_download/en_Aalborg_EM20220601_GFC.pdf
GFC17, S#553673-1 | Aalborg | 0-5 V | 4-20 mA | ±0.01 L/min | 1 sec | 15-pin | Control the flow of H2 into the system | https://www.aalborg.com/images/file_to_download/A_GFC%20Manual%20TD9709M%20Rev%20T.pdf
HFC-D-302B, S#0975944001 | Teledyne Hastings | 0-5 V | 4-20 mA | ±0.01 L/min | 1 sec | 9-pin & 24 VDC | Control the flow of HF into the system | https://www.teledyne-hi.com/resourcecenter/Documents/Manuals/151-HFM-300_HFC-302_Manual.pdf
EZ-Zone PM Panel Mount Controller | Watlow | ? | 0-15 A | ±1 C |  |  | Control the temp of the furnace | file:///C:/Users/kyles/Downloads/pm%20pid%201.pdf
DC Power Suppply 120V 3A | Kungber | ? | 0-3 A | 0.1 V |  |  | Control electricity to the heating tape | https://www.amazon.com/Kungber-Adjustable-Switching-Regulated-Alligator/dp/B0923L6ZT5/ref=sr_1_1_sspa?crid=F4PJMTUEIKTA&keywords=programmable%2B120v%2Bdc%2Bpower%2Bsupply&qid=1656604315&sprefix=programmable%2B120v%2Bdc%2Bpower%2Bsupply%2Caps%2C77&sr=8-1-spons&spLa=ZW5jcnlwdGVkUXVhbGlmaWVyPUEyTUhFT1pFQk8xV0hFJmVuY3J5cHRlZElkPUEwMzM2OTA0M0dONDZESDFNNFBPViZlbmNyeXB0ZWRBZElkPUEwMzYzNjg1MTZLU1pFWVhVTzA4RiZ3aWRnZXROYW1lPXNwX2F0ZiZhY3Rpb249Y2xpY2tSZWRpcmVjdCZkb05vdExvZ0NsaWNrPXRydWU&th=1
Type K Thermocouple MI Cable Probe | EvoSensors | ? | N/A | ±1 C | 1 min | miniature male flat pin | Monitor temperature of the salt
RGA 100 | Stanford Research Systems | ? | N/A | 8 bit (fixed) | 28800 baud (fixed) | 9-pin & 24 VDC | Monitor composition of off gas | https://www.thinksrs.com/downloads/pdfs/manuals/RGAm.pdf
GFG Micro IV G223, S#21056882 & GFG DI220, S#21062601 | Good for Gas | ? | N/A | 1 ppm | 1 sec | USB | Detect Leaks of HF outside the system
Diffuse Reflection Sensor | IFM | 0-2.5 V | N/A | ? | 10 msec | M12 | Detect whe nthe GFG Micro IV has tripped | https://www.ifm.com/download/files/ifm-OGH580-20190312-IODD11-en/$file/ifm-OGH580-20190312-IODD11-en.pdf
BC60 Parcel Scale | Mettler Toledo | 0-5 V | N/A | ±0.1 kg | 1 sec | H-5275-USB | Monitor weight of transfer vessel | https://www.mt.com/us/en/home/library/operating-instructions/industrial-scales/GSP_BC_Scale_SM.html
KJLC 345 Series Hot Filametnt Ion gauge | Kurt Lesker | 0-9 V | N/A | ± 1 μPa | 1 min |  | Measure vacuum pressure | https://www.lesker.com/newweb/gauges/pdf/11-237-ig-ds-kjlc354seriescontroller.pdf
Means not connected
|  | Input/Output: |  |  |  |  | everything is analog
Means probably wont connect |  | · Corrosive Gas flow controller
· 2 Non-Corrosive gas flow controllers
Means has direct computer connection |  | · Furnace controller (maybe)
· Power supply (maybe)
o 3 guaranteed, but up to 5
Input only:
· Thermocouple
· RGA
· HF Detector camera
· Scale
· H2 Detector camera (maybe)
· pH monitor or camera (maybe)
o 4 guaranteed, but up to 6

## Electrocell
[8 empty] | low | high
[7 empty] | Proposed Total | 14673.08 | 19212.28
[7 empty] | Spent total | 18393.01
Equipment | Brand | Model | Cost | Quantity | Total | Specifications | Purpose | Used in Build | Lead Time | Posession Status | Quote / Webpage
Electrochemical Workstation | Gamry Instruments | Interface 1010E | 8500 | 1 | 8500 | ±1A max, ±12V max, EIS 10μHz - 2MHz | measure electrochemical potenitals | yes |  | arrived | https://www.gamry.com/cyclic-voltammetry/#:~:text=Cyclic%20Voltammetry%20(CV)%20is%20the,like%20the%20Gamry%20Interface%201010B. | 8500
Glassy Carbon Crucible | EMC Industries (HTW) | GAZ 92 | 3600 | 1 | 3600 | 88 mm OD, 82 mm ID, 175 mm L, 920 mL -or- 86 mm OD, 80 mm ID, 127 mm L, 570 mL | Contain molten salt | yes | 2 weeks | arrived | ..\..\Downloads\4.11.2023 Quote Texas A&M University.pdf | 3600
Glassy carbon rod | EMC Industries (HTW) | Rod | 1441 | 1 | 1441 |  | Counter electrode | yes |  | arrived | ..\..\Downloads\4.11.2023 Quote Texas A&M University.pdf | 1441
Platinum wire | Surepure Chemetals | Pt-wire016-02 | 199.8 | 1 | 199.8 | 26 gauge (0.4 mm), 99.95% pure, 2ft long | Reference electrode | yes |  | arrived | https://www.surepure.com/Pt-wire016-02/p/3501 | 199.8
Alumina sheet | Mcmaster-Carr | 8978T65 | 212.5 | 1 | 212.5 | 6" L, 6" W, 1/4" T | Insulate crucible from vessel | yes | 1 day | arrived | ..\..\Downloads\Electrocell_McMaster-Carr.pdf | 212.5
+ machining costs
Alumina tube | Mcmaster-Carr | 8746K352 | 38.74 | 1 | 38.74 | 1/4" OD, 1/8" ID, 24" L | Insulate electrodes | yes | 1 day | arrived | ..\..\Downloads\Electrocell_McMaster-Carr.pdf | 38.74
Alumina tube | Mcmaster-Carr | 8746K362 | 39.72 | 1 | 39.72 | 1/4" OD, 0.156" ID, 24" L | Insulate electrodes | yes | 1 day | arrived | ..\..\Downloads\Electrocell_McMaster-Carr.pdf | 39.72
Alumina tube | Mcmaster-Carr | 87175K12 | 47.85 | 1 | 47.85 | 1/16" OD, 0.016" ID, 18" L, 2 holes | Insulate reference electrode | no | 1 day | arrived | ..\..\Downloads\Electrocell_McMaster-Carr.pdf | 47.85
Copper tube | Mcmaster-Carr | 8967K88 | 11.29 | 1 | 11.29 | 1/4" OD, 0.032" WT, 6' L | Offgas tubing | yes | 1 day | arrived | ..\..\Downloads\Electrocell_McMaster-Carr.pdf | 11.29
PVFD tube | Mcmaster-Carr | 51105K21 | 35.6 | 1 | 35.6 | 1/4" OD, 1/8" ID, 10' L | Ar tubing | yes | 1 day | arrived | ..\..\Downloads\Electrocell_McMaster-Carr.pdf | 35.6
+ shipping | Mcmaster-Carr |  | 59.61 | 1 | 59.61 | [6 empty] | 59.61
316SS Tube fitting | Swagelok | SS-400-6-2BT | 17.42 | 2 | 34.84 | 1/4" to 1/8", bored through | hold electrodes | yes |  | arrived | https://products.swagelok.com/en/c/straights/p/SS-400-6-2BT | 34.84
316SS Tube fitting | Swagelok | SS-400-6-1BT | 18.69 | 1 | 18.69 | 1/16" swagelok to 1/4" male NPT, bored through | hold reference electrode | yes |  | arrived | https://products.swagelok.com/en/c/straights/p/SS-400-6-1BT | 18.69
316SS Tube fitting | Swagelok | SS-400-1-4BT | 11.36 | 3 | 34.08 | 1/4" swagelok to 1/4" male NPT, bored through | hold insulating tubes | yes |  | arrived | https://products.swagelok.com/en/c/straights/p/SS-400-6BT | 34.08
PTFE ferrules | Swagelok | T-400-SET | 3.96 | 10 | 39.6 | 1/4" | hold electrodes | yes |  | arrived | https://products.swagelok.com/en/c/ferrule-sets/p/T-400-SET | 39.6
PTFE ferrules | Swagelok | T-200-SET | 4.84 | 5 | 24.2 | 1/8" | hold reference electrode | yes |  | arrived | https://products.swagelok.com/en/c/ferrule-sets/p/T-200-SET?q=:relevance:bodyMaterial:PTFE:connection1Size:1%2F8+in. | 24.2
PTFE ferrules | Swagelok | T-100-SET | 7.64 | 2 | 15.28 | 1/16" | hold reference electrode | yes |  | arrived | https://products.swagelok.com/en/c/ferrule-sets/p/T-100-SET | 15.28
Thermowell | Parr Instrument | 265HC | 100 | 1 | 100 | 3.53" OAL | Contain thermocouple | yes | 1 week | arrived | ..\..\Downloads\7004032302-265HC 48HCCN-Texas A&M University-Kyle Williams.pdf | 100
High temp thread seal | DEACON Industries | 8875-THIN | 177.29 | 1 | 177.29 | 4 oz can | Seal NPT threads on autoclave | yes | 4-5 days | arrived | https://www.jetlube.com/product/deacon-8875-thin-thermal-reactive-paste-sealing-compound | 177.29
Plug adapter | AC WORKS | V-DUO | 42.99 | 1 | 42.99 | NEMA L6-30P to 2 NEMA 6-20R | Supply proper power to furnaces | yes | 1 week | arrived | https://www.amazon.com/AC-WORKS-250Volt-Locking-Connector/dp/B08BY4SNQ8/ref=sr_1_6?keywords=250v%2Bplug%2Badapter&qid=1681327990&sr=8-6&th=1 | 42.99
316SS Tube fitting | Swagelok | SS-400-9 | 21.32 | 5 | 106.6 | 1/4" elbow | refill inventory | no |  | arrived | https://products.swagelok.com/en/c/90-degree-elbows/p/SS-400-9 | 106.6
316SS Tube fitting | Swagelok | SS-400-R-8BT | 16.18 | 2 | 32.36 | 1/4" swagelok to 1/2" tube adapter, bored through | Transfer vessel connetions | maybe |  | arrived | https://products.swagelok.com/en/c/90-degree-elbows/p/SS-400-9 | 32.36
316SS ferrules | Swagelok | SS-400-SET | 2.53 | 10 | 25.3 | 1/4" | refill inventory | no |  | arrived | https://products.swagelok.com/en/c/ferrule-sets/p/SS-400-SET | 25.3
316SS ferrules | Swagelok | SS-200-SET | 3.08 | 10 | 30.8 | 1/8" | hold electrodes | maybe |  | arrived | https://products.swagelok.com/en/c/ferrule-sets/p/SS-200-SET | 30.8
PTFE Tube fitting | Swagelok | T-400-6-2 | 24.15 | 2 | 48.3 | 1/4" to 1/8" | hold electrodes | maybe |  | not ordered | https://products.swagelok.com/en/c/straights/p/T-400-6-2 | 0
Needle valve | Swagelok | SS-3HNRS4-G | 415.7 | 2 | 831.4 | 1/4" connection, severe service, grafoil packing | Connect purified salt transfer vessel to electrochem cell | maybe |  | arrived | https://products.swagelok.com/en/c/straight-pattern-regulating-stem/p/SS-3HNRS4-G?q=:relevance:connection1Size:1%2F4+in. | 831.4
Copper tube | Mcmaster-Carr | 8967K88 | 11.29 | 2 | 22.58 | 1/4" OD, 0.032" WT, 6' L | refill inventory | no | 1 day | arrived | ..\..\Downloads\Electrocell_McMaster-Carr.pdf | 22.58
Copper sheet | Mcmaster-Carr | 8964K32 | 44.67 | 1 | 44.67 | 24" L, 4" W, 1/16" T | Liner for purified salt transfer vessel | maybe | 1 day | arrived |  | 44.67
304SS half nipple | LDS Vacuum | 462-300-LF | 156 | 1 | 156 | 4.62" Flange OD, 3" Tube OD, 3.53" OAL | Purified salt transfer vessel | maybe |  | arrived | https://www.ldsvacuumshopper.com/462flangeod3.html | 156
304SS blank flange | LDS Vacuum | 462-000 | 89 | 1 | 89 | 4.62" OD, 0.75" T | Purified salt transfer vessel | maybe |  | arrived | https://www.ldsvacuumshopper.com/458odblank.html#_ga=2.219534233.1816599746.1680189768-672292880.1680033449 | 89
+ machining costs | Custom Fabricators |  | 350 | 1 | 350 | [6 empty] | 350
Band Heater | TEMPCO (Grainger) | BCH06426 (2VYU3) | 83.54 | 1 | 83.54 | 3" ID, 3" L, 240V, 3.33 A, 760C | Heater for purified salt transfer vessel | maybe |  | arrived | https://www.grainger.com/product/TEMPCO-Band-Heater-3-in-Inside-Dia-2VYU3 | 83.54
Molybendium wire | GOONSDS (Amazon) |  | 16.88 | 1 | 16.88 | 26 gauge (0.4 mm), 99.99% pure, 1m long | Potential reference electrode | maybe |  | arrived | https://www.amazon.com/gp/product/B09FLPR8Q6/ref=ox_sc_act_title_1?smid=A3B3XE1QENUE52&psc=1 | 16.88
Thermowell seal | Parr Instruments | 48HCCN | 6.4 | 1 | 6.4 |  | refill inventory | no | 1 week | arrived | ..\..\Downloads\7004032302-265HC 48HCCN-Texas A&M University-Kyle Williams.pdf | 6.4
Thermocouple | Parr Instuments | A472E4 | 54 | 1 | 54 | 5.5" stem | monitor salt temp | maybe | 1 week | arrived | https://www.parrinst.com/products/stirred-reactors/options-accessories/thermocouples/ | 54
Cart | Uline | H-3037 | 425 | 1 | 425 |  | house experiment | maybe |  | not ordered | https://www.uline.com/BL_595/Uline-Welded-Steel-Flat-Shelf-Carts | 0
Vacuum pump | Edwards (Ebay) | RV3 | 566.07 | 1 | 566.07 | standard | chamber purging | maybe |  | arrived | https://avac.com/product/boc-edwards-vacuum-pump-40-22618-02-rv5-rebuilt/ | 566.07
Neoprene rubber pad | Mcmaster-Carr | 1370N39 | 48.23 | 1 | 48.23 | 12" L, 12" W, 1/2" T | reduce pump vibration | maybe | 1 day | arrived | ..\..\Downloads\Electrocell_McMaster-Carr.pdf | 48.23
304SS Tube fitting | LDS Vacuum | NW25x25SWG | 95 | 2 | 190 | 1/4" swagelok to KF25 | Connect pump to tubing | maybe |  | arrived | https://www.ldsvacuumshopper.com/nw25to14tubeod2.html | 190
Glassy carbon lid | EMC Industries (HTW) | GAD 3 | 283 | 1 | 283 | 90 mm OD, 17 mm H | to cover the crucible | maybe |  | not ordered | ..\..\Downloads\4.11.2023 Quote Texas A&M University.pdf | 0
Power cord | Yuduo |  | 20.88 | 1 | 20.88 | NEMA 6-15P to NEMA 6-15R | to connect the band heater to the variac | maybe | 1 week | arrived | https://www.amazon.com/6-15P-Plug-Straight-Blade-Power/dp/B00474CZIK | 20.88
Variable electric transformer | Superior Electric | 3PN216C | 973 | 1 | 973 | 0-280V, 3.5A, 50/60HZ, NEMA 6-15 plug and receiver | to control the temperature of the band heater | maybe | 8-12 weeks | ordered | https://us.rs-online.com//product/superior-electric/3pn216c/70120697/?gclid=CjwKCAjwrdmhBhBBEiwA4Hx5g7tGxbeUdEFUa95egxqhs0JGYOXoiD_qod5DnO_XDI2GBdWkxfW2DBoCibIQAvD_BwE&gclsrc=aw.ds | 973
Alumina tube | Mcmaster-Carr | 8746K452 | 72.22 | 1 | 72.22 | 1/16" OD, 1/32" ID, 24" L | hold reference electrode | yes | 1-2 days | ordered | https://www.mcmaster.com/products/tubing/?s=alumina+ceramic+tubing | 72.22
Alumina adhesive | MTI Corporation | 634AL6 | 62.97 | 1 | 62.97 | 6 oz, high purity | seal alumina tubes | yes | 4-6 days | ordered | https://www.mtixtl.com/1760C3200FHi-PurityAluminaCoating1Quart-EQ-634-AL-LD.aspx | mti